## Sheet1
Task Name | FrontEnd Owner | Front End | BackEnd Owner | BackEnd | Intgeration | EndDate
Institute Reg | Hanik, Vaibhav (BootStrap) + Himanshu | Reg Form (Angular + BootStrap) Test On All Kind of Devices , and Test on All kind of Browsers | Hanik | Express + Mongoose + Modular (Connection , Config , Routes , Schema) + Logging | Himanshu + Hanik | 2016-03-25
Institute Login | Hanik, Vaibhav (BootStrap) + Himanshu | Reg Form (Angular + BootStrap) Test On All Kind of Devices , and Test on All kind of Browsers | Hanik |  | Himanshu + Hanik | 2016-03-25
Inst Admin Register | Harsh |  | Lakshit |  | Harsh + Lakshit | 2016-03-25
Admin Login | Harsh Category wise Option |  | Lakshit |  |  | 2016-03-25
Category (1st) | Himanshu/Kuldeep | CRUD in Category |  |  |  | 2016-03-25
Add Course (Admin) | Himanshu/Kuldeep | CRUD in Course |  |  |  | 2016-03-25
Add User | Himanshu/Kuldeep | Teacher , Student |  |  |  | 2016-03-25
Assign Courses to Teacher | paritosh, rohit |  | sunil/geetansh |  |  | 2016-03-25
Test Develop (Teacher Module) | paritosh, rohit |  | sunil/geetansh |  |  | 2016-04-02
Questions Develop (Teacher Module) | paritosh, rohit |  | sunil/geetansh |  |  | 2016-04-02
Student Register | Vidhu/Manish |  | sunil/geetansh |  |  | 2016-03-25
Teacher Video Upload / Doc Upload / PPT Upload | Kuldeep/Tushit/Akshay | Sequence Decide, Video Upload | vaibhav/sunil/geetansh
Test Engine (Student Module) | Hanik,Rohit V,Tushit/Akshay |  | vaibhav/sunil/geetansh |  |  | TBD